## Checklist
PPP Feasibility Study Checklist
Project Name
No | Sector | Yes/No Partly | Discriptions
A | Summary
A1 | Project Discription in briefe
B | Market Study
B1 | Have current and future supply analysis been prepared?
B2 | Have the supply and demand show a market gap?
B3 | Has the Pricing Strategy been Prepared?
B4 | What does SWOT Analysis show?
B5 | Have the potential investors been identified?
C | Engineering and Technical Study
C1 | Project Location
C2 | Has the project site or options for the site options been identified?
C3 | Has an impact and management strategy been prepared to deal with the major technical and operational risks to the project?
C4 | Based on the analysis, does the sponsoring authority consider the project concept to be practical?
C5 | Has the Assessment of existing supply been prepared?
C6 | Is the project site or at least one of the project site options suitable from a technical and operational perspective?
C7 | Has the technical scope of the project been defined?
C8 | Is the engineering plan practical?
C9 | Is the operations and maintenance plan practical?
C10 | Have the major technical and operational risks to the project been identified?
C11 | Does the project master plan prepared?
C14 | Have the costruction cost estimates prepared?
C15 | How much is the project total cost?
C16 | Hav IT & Office Equipment plan prepared?
C17 | How much start up cost does need the project?
D | Financial Study
D1 | Have all major project cost components (capital, operations, maintenance) of the technical scope of the project been estimated?
D2 | Are the assumptions on major project cost components reasonable? Can they be justified based on a rationale?
D3 | Has a market demand analysis been done? (Tariffs, Volume)
D4 | Are the assumptions on tariff/prices reasonable? Can they be justified based on a rationale?
D5 | Will the users be willing to pay the proposed tariff/ prices?
D6 | Are the assumptions on volume/quantity of usage reasonable? Can they be justified based on a rationale?
D7 | Have similar projects that were done in the past been analysed for project cost, tariff/prices and volume/quantity of usage?
D8 | Are the assumptions in the proposed project comparable to similar projects that were done in the past? If not, then can the assumptions be justified on sound economic rationale?
D9 | Has an estimate of required financial support from the public sector been made?
D10 | Have the major financial and commercial risks to the project been identified?
D11 | Have the impact and management strategy of the financial and commercial risks to the project been prepared?
D12 | Does the financial analysis demonstrate that the sponsoring authority will recover its investments along with a reasonable return under different scenarios?
D13 | Based on the analysis, does the sponsoring authority consider the project concept to be financially and economically viable?
D14 | Has a strong rationale and recommendation been made by the sponsoring authority in the preliminary assessment?
D15 | Have the likely economic benefits generated by the project been identified?
D16 | Has a sensitivity analysis been undertaken?
D17 | Have the key financial and economic ratios been computed? (for example, NPV, IRR,EIRR, ENPV etc.)
D18 | Have financial projections been prepared?
D19 | Has a financial analysis model been used to assess the financial viability of the project?
D20 | Has the fiscal affordibility of the project is identified?
D21 | Have the financial statements of the project is prepared?(for example, Balance sheet, income statement...)
D22 | Have the producer suplus and consumer suplus analysis for infrastructure project is prepared?
E | Legal Study
E1 | Land Ownership and Construction
E2 | Process for Getting Land
E3 | Tax and tariff examption
F | The Social, Economic and Environmental Study
Has a scoping environmental assessment been done? Were any serious issues raised?
Has an impact and management strategy been prepared to deal with the major social and environmental issues?
F1 | Has a scoping social impact assessment been done? Were any serious issues raised?
G | Value For Money Study
G1 | Has the project Value for Money Analysis been preapared?
H | Risk Management
H1 | Major Risks associated to the project
H2 | Risk Sharing and allocation
H3 | Risk Mitigation
I | Base Case Assumptions
H2
J | Conclusion Statement
I1