## Checklist
Project name:
No. | Item | Yes/ No/ Partly | Comments
A | Needs and options analysis
A1 | Does the proposed project meet the present or future needs of the public? Have the likely benefits to users been identified?
A2 | Does it meet the objectives of the sponsoring authority and wider policy goals? Does the project fit within strategic plans?
A3 | Have a number of different options been identified to deliver the service/facility/product?
A4 | Have those options been compared from technical, land & resettlement, environmental & social, and private sector interest perspectives? Has a preferred option been identified?
A5 | Have alternatives to new asset development been considered (i.e. use of existing assets and non-asset solutions)?
A6 | Has value for money been assessed (i.e. the cost to the public sector of developing the project as PPP versus conventional public sector procurement)?
B | Technical and operational feasibility
B1 | Has the project site or options for the site options been identified?
B2 | Is the project site or at least one of the project site options suitable from a technical and operational perspective?
B3 | Has the technical scope of the project been defined?
B4 | Is the preliminary engineering plan practical?
B5 | Is the operations and maintenance plan practical?
B6 | Have the major technical and operational risks to the project been identified?
B7 | Has an impact and management strategy been prepared to deal with the major technical and operational risks to the project?
B8 | Based on the preliminary analysis, does the sponsoring authority consider the project concept to be practical?
C | Environmental and social safeguard assessments
C1 | Has a scoping social impact assessment been done? Were any serious issues raised?
C2 | Has a scoping environmental assessment been done? Were any serious issues raised?
C3 | Has an impact and management strategy been prepared to deal with the major social and environmental issues?
D | Financial and economic viability
D1 | Have all major project cost components (capital, operations, maintenance) of the technical scope of the project been estimated?
D2 | Are the assumptions on major project cost components reasonable? Can they be justified based on a rationale?
D3 | Has a preliminary market demand analysis been done? (Tariffs, Volume)
D4 | Are the assumptions on tariff/prices reasonable? Can they be justified based on a rationale?
D5 | Will the users be willing to pay the proposed tariff/ prices?
D6 | Are the assumptions on volume/quantity of usage reasonable? Can they be justified based on a rationale?
D7 | Have similar projects that were done in the past been analysed for project cost, tariff/prices and volume/quantity of usage?
D8 | Are the assumptions in the proposed project comparable to similar projects that were done in the past? If not, then can the assumptions be justified on sound economic rationale?
D9 | Have preliminary financial projections been prepared?
D10 | Has a financial analysis model been used to assess the financial viability of the project?
D11 | Has an estimate of required financial support from the public sector been made?
D12 | Have the key financial ratios been computed? (for example, NPV, IRR, etc.)
D13 | Have the major financial and commercial risks to the project been identified?
D14 | Have the impact and management strategy of the financial and commercial risks to the project been prepared?
D15 | Has a sensitivity analysis been undertaken?
D16 | Does the preliminary financial analysis demonstrate that the sponsoring authority will recover its investments along with a reasonable return under different scenarios?
D17 | Have the likely economic benefits generated by the project been identified?
D18 | Based on the preliminary analysis, does the sponsoring authority consider the project concept to be financially and economically viable?
D19 | Has a strong rationale and recommendation been made by the sponsoring authority in the preliminary assessment?
E | Screening for PPP suitability
E1 | Has the project been screened for PPP suitability, including (1) assessing how supportive the PPP environment is and (2) how suitable the project is for PPP? What was the result?
E2 | Have the main barriers to PPP that were raised in the screening been clearly identified?
E3 | Has a preliminary risk management plan been prepared to address these barriers?
F | Possible arrangements for private sector participation
F1 | Has the role of the private sector (direct or indirect investment, indicative PPP mode, etc.) been identified?
F2 | Has an indicative project structure or contractual framework for the PPP arrangement been prepared?
F3 | In selecting a project structure, were different project structures / PPP models considered and evaluated? Was public financing also considered?
F4 | Has the procedure for inviting private sector participation been identified?
F5 | Will the procedure encourage competition in the private sector?
F6 | Has the major legal documentation required to allow participation of the private partner(s) been identified?
G | Next steps
G1 | Has an estimate of resources (financial, external expertise) to complete the feasibility study and selection of PPP been made?
G2 | Are budgets available for the above?
G3 | Have all the parties that will be responsible in the next steps, been identified? Such as within sponsor agency, provincial departments and other parties.
G4 | Have the roles and responsibilities of involved parties been prepared?
G5 | Is there an agreement amongst involved parties in undertaking their respective roles and responsibilities?
G6 | Has the time frame required for completing the feasibility study and selection of PPP been estimated?
G7 | Is the time frame reasonable and practical?